GENERAL TIMELINE FOR 2007 RMS MEETING

As of: August 16, 2007

| Months Prior | Date | # WHO | Item |
| --- | --- | --- | --- |
| 20-15 | 5-06 |  | Organize committee chairs and develop a theme and logo. |
| 17-13 | 4-24-06 |  | Walk-through of convention facilities with organizing committee (at Snowbird). |
| 17-16 | 6-1-06 |  | Prepare Call-for-Session Chairs and ad to be printed in Billings meeting packet. Promotional graphics for Billings meeting final program. Setup bank account for meeting. |
| 13 | 9-1-06 |  | Finalize Session Chairs and general program. Get convention manager on board. |
| 12 | 10-1-06 |  | Mail Call-for-Papers and advertise call through various affiliates and “sister” organizations. Draft budgets due for all committees. |
| 11 | 12-5-06 |  | Submit pdf of 1/4 page add for Explorer. Get post card mailer out to all Section members. |
| 11 | 12-5-06 | Sponsor | Start soliciting sponsors |
| 10 | 1-4-07 | Finance | Committee chairpersons finalize plans and budgets. Based on budget, finalize registration fee and attendance estimate. Confirm liability insurance for the event. |
| 10 | Jan 2007 | Exhibits | Finalize Exhibitor forms. Final Contract with GES. Email/send out prospectus/registration forms to past exhibitors. |
| 9 | Feb 2007 | Finance | Finalize Budget |
| 9 | Feb 2007 | Exhibit | GES to create exhibit area layout |
| 9 | Feb 2007 | Tech Prog. | Have online abstract service fully functional. |
| 8 | 3-1-07 | Reg. | Have online registration contractor contracted/finalized. |
| 8 | 3 - 2007 | Tech Prog. | Co-chairs recruit for presentations /papers/posters |
| 8 | 3-9-06 | Publicity | Flyer for AAPG annual meeting designed and ready. Arrange for insert in reg. packet and available at UGS and AAPG booths. |
| 6 | 4-20-07 | Tech Prog. | Abstract deadline: Receipt of abstract notification should be sent to authors. Evaluation of abstracts for accept/reject by Technical Program committee. Final program organization. |
| 6 | 4-30-07 | Tech Prog. | Acceptance/rejection letters mailed and Speaker/poster kits updated and prepared. |
| 4 | 6-07 | Chair/ Publicity | Invitations and meeting schedules sent to National officers, officer candidates, Division Presidents, Chairman of the House of Delegates, and AAPG Executive Director. Need to receive their confirmation of attendance. |
| 4 | 6-07 | Publicity | Explorer ad submitted. Deadline for abstracts to be published in Bulletin |
| 4 | 6-07 | Chair/ Publicity | Invitations and meeting schedules sent to National officers, officer candidates, Division Presidents, Chairman of the House of Delegates, and AAPG Executive Director. Need to receive their confirmation of attendance. |
| 4 | 6-07 | Publicity | Explorer ad submitted. Deadline for abstracts to be published in Bulletin |
| 4 | 6-15-07 | Publicity/ Tech Prog./ Registration/Chair/WL | Meeting announcement mailed. Consider pocket program. Order e-mail blast from AAPG. Speaker/poster kits mailed. On-line registration up and running. Be sure all dignitaries and invitees receive meeting announcement. Develop detailed checklist for remainder of meeting process discussed at an Organizing committee meeting. |
| 3 | 7-2007 | Publicity | Submit 2nd Explorer ad for publication in August |
| 2 | Aug 15 2007 | Julie | All speaker’s abstracts to Western Leisure - forwarded to Stephanie |
| 2 | Aug 17 2007 | Western Leisure | Send exhibitor list in Excel to GES to send out Exhibitor Kit GES to email exhibitor kit to exhibitors |
| 2 | Aug 17 |  | Registration Deadline to received UGA Guidebook on Central Utah |
| 2 | August 17 | Western Leisure | ### Addressing & Mailing of invitation to President’s Reception |
| 2 | August 24 | ALL | ### Menu’s to Julie (julies@westernleisure.com) |
| 2 | August 24 | ALL | ### Volunteers to Jessica (jallulee@gmail.com) |
| 2 | August 24 | Chair/ Tech Prog. | Final room assignment of sessions, speaker room, registration, guests hospitality rooms, poster sessions, etc |
| 2 | August 24 | Western Leisure | Design for admission to social functions (could be sent to printer with Signage) |
| 2 | August 24 | Signs | Draft list of preliminary/all sign needs. Receive bids from 2 printers. (Check easel count with Snowbird or order easels) |
| 2 | Monthly | Publicity | Email reminder about meeting (if in need of more attendees) |
|  | Aug 24 | ALL | Committee Meeting 10am DNR |
| 2 | Aug - Weekly | ## WL | Review sleeping room pick-up (weekly) |
| 2 | Aug 2007 | Publicity | Submit 3rd Explorer ad for publication in September. |
| 1 | Sept 4, 2007 | Technical Committee | Final details send to speakers/session chairs. |
| 1 | Sept 4, 2007 | Short Courses/ Field Trips | Cancel field trips/short courses if necessary |
| 1 | Sept 4, 2007 | Exhibit | Determine Security Needs. (Using Snowbird Security) |
| 1 | Sept 4, 2007 | Signs | Final Design/layout all signage |
| 1 | Sept 4, 2007 | Tech Prog./ Julie | Confirm/Finalize all AV needs. |
| 1 | Sept 4, 2007 | Awards | Order awards for recipients |
| 1 | Sept 4, 2007 | Sponsor | ### Receive all sponsors logos to be used in program & signage |
| 1 | Sept 4, 2007 | Judging | Find & Confirm judges. PBA note: this date will have to be after the close of registration. |
| 1 | Sept 4, 2007 | Short Course/ fieldtrip | Send confirmation/details to registered participants. Reconfirm details. Drivers of field trips approved by AAPG. Won’t be necessary because sponsored by UGA |
| 1 | Sept 4, 2007 | ### WL | Order coach for Park City Tour |
| 1 | #### Sept 7, 2007 | ALL/ Publicity | Submission date for copy for meeting announcement |
| 3 weeks | Sept 14 2007 |  | Early Registration Deadline |
| 3 weeks | Sept 14 2007 | Publicity | Final program to printer. Contact SL Convention Bureau about a welcome at SLC airport and arrange for materials for bag stuffing. |
| 3 weeks | Sept 14 2007 | Tech Prog. | Reconfirm all Speakers & their requirements |
| 3 weeks | Sept 14 2007 | WL | Print all tickets for all meeting functions |
| 3 weeks | Sept 14 2007 | Tech Committee | Order Speaker gifts |
| 3 weeks | Sept 14 2007 | Signage | Order Signage |
| 3 weeks | Sept 14 2007 |  | Deadline for advanced registration. Cancel any unused rooms (We have passed our commitment already.) |
| 3 weeks | Sept 14 2007 | WL | Finalize F&B choices to Snowbird |
| 3 weeks | Sept 14 2007 | Volunteer | Make volunteer assignments. |
| 3 weeks | Sept 14 2007 | Tech committee/ Julie | Logistics to GES & order snowbird staff for pick-up/delivery of Core to/from Snowbird |
| 2 weeks | Sept 20 2007 | Western Leisure | CD’s printed for attendees |
| 2 weeks | Sept 20 2007 | Registration | Prepare badges for all non registered staff (speakers, comp registrations, staff, volunteers, etc) |
| 2 weeks | Sept 21 2007 | Judging | Prepare & print conference/session evaluation forms |
| 2 weeks | Sept 24 2007 | Registration | Prepare badges for all reregistered attendees & any non registered attendees (guest speakers, volunteers, comp. Registrations, etc..) |
| 2 weeks | Sept - Weekly | ## Western Leisure | Review sleeping room pick-up (weekly). At some point we need to assign the comp rooms. We likely should give one of these to the AAPG President and Ex Director. Julie do you want one? I would like one if available. |
| 2 weeks | Sept - Weekly | ## Finance | Review Budget |
| 1 week | October 1 | Registration | Preparation of registration badges & packets |
| 1 week | October 2 | ALL | Last Meeting |
| 1 week | October 2 | Western Leisure | Guarantee count for F&B to Snowbird |
| 1 week | October 2 | Paul, Julie | Establish onsite staff meeting schedule & required attendance list |
| During meeting | Oct 5/6 | Paul, Julie (TBD) | Onsite Precon with Snowbird (Friday afternoon or Sat) |
| During meeting | Oct 6 2007 | Volunteer /Registration | Preparation & stuffing of Convention Bags |
| ##### During meeting | Oct 6th or 7th | Volunteers | Conduct meeting instructional briefing for volunteers |
| During meeting | Oct 7-9 | Finance | Arrange daily invoice review with Snowbird |
| During meeting | Oct 9 | Paul, Julie, etc.. | Conduct post con with Snowbird |
| 1 week after | Oct 15, 2007 | ALL | Prepare list for thank you letter’s, send out letters |
| 1 week after | Oct 15, 2007 | Tech committee | Prepare summary reports on evaluation forms |
| 1 month after | Oct 2007 | Roger | Review each invoice received, break down into appropriate meeting categories and schedule payments |
| 1 month after | Oct 2007 | Roger | Prepare preliminary financial reports |
| 1 month after | November 1 | ALL | Summary/final reports from each committee chair to pass to future committee chair |
| 1 month after | November 8 | ALL | Post Convention Party |
| 2-3 months after | Nov/Dec 2007 | Roger | Prepare final financial reports |
| 2-3 months after | Nov/Dec 2007 | Paul | Distribute final meeting reports to 2008 committee |