## Agenda
| Nicole Chattin - Registration 619-244-6801 | [6 empty] | Event Name: | AAPG Rocky Mountain Meeting
[8 empty] | Client Name: | AAPG - RMS
[8 empty] | Event Date(s): | October 5 - 12, 2007
[8 empty] | Event Location: | Snowbird Resort
[8 empty] | Estimated Attendees: | 600 ppl
[8 empty] | Prepared By: | Julie T Sibthorp & Paul Anderson
AAPG - Rocky Mountain Section Meeting Agenda
|  | LOCATION | HOURS | COMMITTEE | # PPL | HOTEL/SET UP | FOOD AND BEVERAGE | AUDIO VISUAL | Entertainment/ Activity
Day 1 - Friday, October 5, 2007
| Field Trip #1 - Structural Geo | DNR Building | 7:00 |  | 28 | Richfield Utah | Provided by leaders
| GES to transfer Core to Snowbird | Utah Core Research Center | 9:00am pick -up; depart 9:45am Tentative | Mike Laine 824-9013
| Snowbid Staff to transport Core to Core Presentation Areas | Drop off at Cliff then continue to Snowbird Center for delivery to room Cottonwood C&D | 10:45am - noon |  |  | Need 2 staff at $40 per hour to transfer Core (as directed by AAPG staff) to storage area in cliff Lodge and to CottonWood C&D in Snowbird Center. Need 16 tables in Cottonwood room
Day 2 - Saturday, October 6, 2007
| Short Course #1 Leadville | UGS | 10:00am-3:00pm
| Dry run for Joe & Volunteers for Tram Luncheon | Tram | Moved to Sunday
| Little Pine |  | 12:00pm - 6:00pm |  |  | Two tables and 4-5 chairs. Need approx. Place 37 easles in room to be used as needed. |  | internet access
| Short Course #2 Shale-gas (session 2) | Snowbird Center, Cottonwood C & D | 1:00pm-5:00pm | Mike Laine 824-9013 | 32 | Classroom style for 31 , will need 16 tables set for core display . Need Easle outside Room | CO4 - Take a hike Executive Break ($7.95 per person) at 3:00pm for 30 minutes | LCD Projection Package Technician (1 hr only for 1st hour) Laptop
| Precon Meeting | Wasatch A Room | 2:00pm | Julie Sibthorp 801-643-9398 Paul Anderson 301-2823
| "Rocks in your head" | Utah Geological Survey | 8:30am - 4:00pm | Sandy Eldridge 537-3325 | 40ish |  | Sandy to coordinate lunch
Day 3 - Sunday, October 7, 2007
| Dry run for Joe & Volunteers for Tram Luncheon | Tram | TBD
| GES - Set up Booths & Poster Boards | Ballroom 2, Mezanine Lobby, Atrium Overlook, Golden Cliff, Magpie A&B | 6:00am - 12:00pm | Julie Sibthorp 801-643-9398 Mike Allen (GES) 801-330-7196 |  |  |  | Routers for wireless internet
| Conference office | Little Pine | 7am-10pm |  | 4 | Two tables and 4-5 chairs. Need approx. 15 easles to be placed in this room to be used at vaious locations for signage. | Water station | Wireless Internet Connection
| Field Trip #2 Wasatch Front departs | Bottom of Escalators | 8:30am | Brad Hill 631-1618 | 27
| Short Course #2 Shale-gas (session 1) | Snowbird Center, Cottonwood C & D | 10:00am - 3:00pm | Mike Laine 824-9013 | 32 | Classroom, will need 16 tables set for core display at front of room. Need Easle outside Room | BL5- Superior Deli. Lunch at Noon in Cottonwood B | LCD Projection Package Technictian for 1st hour only Laptop Delete - Wireless Lavaliere Mic
| Breakfast | [5 empty] | On Own
| Registration | Coat Room | noon - 8:00pm | Greg Wood 680-7663 Jessica Allen 891-8248 |  | Skirted Tables 4, chairs 4-5. Need Easel |  | 1 Hardwire internet connection for registration computer
| Public Forum | Ballroom 1 | 1:00-3:00 pm | Steve Schamel | 40 for food - might have 100 | Have room set for the 250 for the opening session. Theatre style-front table 5 chairs on riser. Podium for speaker. Need Easel outside Room | Reg & Decaf Coffee, Sodas (billed on consumption), water, sliced fruit display (to serve 30 people) & cheese & cracker tray (to serve 30 people) in back of room | LCD Projection Package Technician Laptop 1 stand mic out on the floor for audience comments & ADD 4 lavalier microphones
| Exhibitor Set Up | Ballroom 2, Mezanine Lobby, Atrium Overlook, Golden Cliff, | 12:00pm - 5:00pm | Julie Sibthorp 801-643-9398 or Craig Morgan 815-1967 | 34 Booths | GES will provide 1 table & power to each booth |  | Routers for wireless internet for each booth
| Core/Poster Set Up By GES | Magpie A&B & Golden Cliff | 6:00am - Noon | Julie Sibthorp 801-643-9398 or Rich Newhart 720-468-1364 | 9 | 4 tables in Magpie & 6 in Golden Cliff. 6 chairs in Magpie & 2 chairs in Golden Cliff. (see diagram)
| Core/Poster Set Up By Presenters | Magpie A&B & Golden Cliff | Noon -5:00pm (Core arrives at 2:30pm) | Rich Newhart 720-468-1364
| GES to transfer Monday's Core to Snowbird | Utah Core Research Cente to Cliff Lodge Loading Dock | Pick up at 1:30pm. Will take 20 min to load truck.
| Snowbid Staff & to assist in transport Core to Golden Cliff & Magpie | Pick up at Cliff Lodge Loading Dock or storage area- take ot Golden Cliff & Magpie | 2:45pm | Julie Sibthorp 801-643-9398 or Rich Newhart 720-468-1364 |  | Need 2 staff at $40 per hour to transfer Core (as directed by AAPG staff) to MagpieA&B & Golden Cliff
| Snowbid Staff to pick up & transport Core from CottonWood D in Snowbird Center to Loading Dock/stotage area | Cottonwood C& D | 4:00pm | Julie Sibthorp 801-643-9398 or Rich Newhart 720-468-1364 |  | Need 2 staff at $40 per hour to transfer Core (as directed by AAPG staff)
| GES to go to Snowbrid Center at 3:30pm & pick up core from short course & bring some of the core to Cliff Lodge | Cliff Lodge - to Snowbird Center - to Cliff Lodge | 3:30pm
| GES depart for Utah Core Research Center | take to Utah Core Research Center | 4:00pm
| GES arrive at Utah Core research Center | Utah Core Research Center | 5:00pm
| Speaker Ready Room | Red Pine | 3:00-6:00 pm | Rich Newhart 720-468-1364 |  | 3 tables W/ 2 chairs at each table. Need Easel outside Room |  | 3 laptops plus 3 AV tech from 3:00pm - 6:00pm
| Guest Hospitality Room | Summit - 10th Floor | 2:30pm - 4:30pm | Tina Blake 435-901-8328 | 80 | Flowers & Newspaper providd by AAPG. Need Easel outside Room | none |  | Welcome & Distribute gift bag,
| Field Trip 2 return | main entrance | 15:00
| Opening Session | Ballroom 1 | 4:30-5:30 pm |  | 100 | Room set for 250 for tomorrow's session. Theatre style facing AV 4. Need Easel outside Room |  | AV 4 (screen), 2 rental computers (primary & back up), 1 projector, 1 podium, 1 audio set-up, 2 AV tech (1 for audio & 1 for computer)
| Opening Night Ice Breaker Reception in the Exhibit Areas | Exhibit Areas | 5:30pm - 7:30pm | Julie Sibthorp 801-643-9398 or Craig Morgan 815-1967 | 600 | Reception /Buffet. Food Station #1 in Ballroom Lobby. Food Station #2 in Atrium Overlook. (5 bars) 1 Bar in Ballroom and 2 Bar in Atrium Overlook. 2 Bars in Ballroom Lobby Need 4 Easels | Station #1 - Mushroom Caps with Sausage (1000), Potstickers with sauce (1000), Assorted Vegi Chips (500) Stations #2 -Breadspread Rosemary/Hummus (1000), salmon Capers (1000), Assorted Vegi Chips (500), 2 Cash Bars 4 bartenders & 4 ticket sellers (2 tickets given to attandees) ADD Passed Mini Blackbean Quaesdilla (1000) with 3 servers.
| Snowbird Security (Need 2 people) | Lock Ballroom 2, patrol Mezz & Atrium Overlook & Golden Cliff Room | 7:30pmSUN - 8:00amMON | Julie Sibthorp 801-643-9398 or Craig Morgan 815-1967
Day 4 - Monday, October 8, 2007
| Registration | Coat Room | 7:00am - 5:00pm | Greg Wood 680-7663 |  | See Sunday's set-up |  | Internet Connection
| Speaker Ready Room | Red Pine | 3:00pm - 6:00pm | Rich Newhart 720-468-1364 |  | 3 tables W/ 2 chairs at each table. Need Easel outside Room |  | 3 computers plus 3 AV tech from 3:00pm - 6:00pm
| Speakers Breakfast | Maybird | 6:30am -7:30am | Rich Newhart 720-468-1364 | 70 | Banquet/Buffet 6 Rounds of 11. Need Easel outside Room | Breakfast Buffet: BB1
| Delegate Breakfast | Superior A | 6:45am - 8:00am | Julie Sibthorp 801-643-9398 | 34 | Rounds of 8 (no head table or podium needed). Need Easel outside Room | Plated Breakfast B1 with OJ, maple Baked link sausage and baked Croissants | none
| Conference Office | Little Pine | 6:30 am-10pm | Julie Sibthorp 801-643-9398 |  | Two tables and 4-5 chairs |  | Wireless Internet Connection
| Spouse Hospitality | Summit - 10th Floor | 7:30am-5:00pm | Tina Blake 435-901-8328 | 100 | Lounge set-up. Flowers, & Newspaper provided by AAPG. . Need Easel outside Room
| Spouse Breakfast | Summit - 10th Floor | 7:30am - 9:00am (Time change or pay overtime) | Tina Blake 435-901-8328 | 100 | Buffet | Continential Breakfast CB3 - Rise & Shine Breakfast
| IP Prospect Room | White Pine | 8:00am - 5:00pm |  |  | Conference Set-up. Water service on side table.
| Technical Sessions Ballroom #1 | Ballroom 1 | 8:00am - 9:50am | Rich Newhart 720-468-1364 | 250Each (Maximum capacity) | Theater. Need Easel outside Room |  | AV 4 (screen), 2 rental computers (primary & back up), 1 projector, 1 podium, 1 audio set-up, 2 AV tech (1 for audio & 1 for computer)
| Technical Sessions Ballroom #3 | Ballroom 3 | 8:00am - 9:30am | Rich Newhart 720-468-1364 | 250 Each (Maximum capacity) | Theater. Need Easel outside Room |  | AV 5 (screen), 2 rental computers (primary & back up), 1 projector, 1 podium, 1 audio set-up, 2 AV tech (1 for audio & 1 for computer)
| Technical Sessions Ballroom Wasatch A&B | Wasatch A&B | 8:00am - 9:50am | Rich Newhart 720-468-1364 | 150 (Maximum capacity) | Theater. Need Easel outside Room |  | Project to large screen with 2 smaller screen feeds (see drawing), 2 rental computers (primary & back up), 1 projector, 1 podium, 1 audio set-up, 2 AV tech (1 for audio & 1 for computer)
| Exhibit Areas Open | Ballroom 2, Mezanine Lobby, Atrium Overlook, Golden Cliff, | 8:00am - 5:00pm | Julie Sibthorp 801-643-9398 or Craig Morgan 815-1967 | 34 |  |  | Routers for wireless internet
| Poster Areas Open | Magpie A&B, & Golden CLiff | 8:00am - 5:00pm | Rich Newhart 720-468-1364 | 5 posters & 2core in Magpie & 2 core in Golden Cliff
| Spouse Field Trip to Park City | bottom of escalators | 8:30am - 5:00pm | Tina Blake 435-901-8328 | 27 |  | lunch on own in PC |  | Luxury home tour. Motercoach to spot at 8:15am with departure at 8:30am.
| Morning Break | Exhibits areas and Ballroom Lobby | 9:30am - 10:15am | Julie Sibthorp 801-643-9398 | 525 | Reception/Buffet in Mezzaine & Ballroom lobby. Need Easel by Food stations | Muffins, Cinnamon Rolls, Fruit Yogurt / Coffee (Regular & Decaf), Tea, Assorted Soft Drinks
| Technical Sessions Ballroom #1 | Ballroom 1 | 10:15am - 11:35pm | Rich Newhart 720-468-1364 | 250 Each (Maximum capacity) | Theater. Need Easel outside Room |  | AV 4 (screen), 2 rental computers (primary & back up), 1 projector, 1 podium, 1 audio set-up, 2 AV tech (1 for audio & 1 for computer)
| Technical Sessions Ballroom #3 | Ballroom 3 | 10:15am - 11:35pm | Rich Newhart 720-468-1364 | 250 Each (Maximum capacity) | Theater. Need Easel outside Room |  | AV 5 (screen), 2 rental computers (primary & back up), 1 projector, 1 podium, 1 audio set-up, 2 AV tech (1 for audio & 1 for computer)
| Technical Sessions Ballroom Wasatch A&B | Wasatch A&B | 10:15am - 11:35pm | Rich Newhart 720-468-1364 | 150 (Maximum capacity) | Theater. Need Easel outside Room |  | Project to large screen with 2 smaller screen feeds (see drawing), 2 rental computers (primary & back up), 1 projector, 1 podium, 1 audio set-up, 2 AV tech (1 for audio & 1 for computer)
| All convention Luncheon | Cottonwood Rm | 11:45 - 1:15pm | Jason Blake 435-901-1169 | 290 (ticketed event) | Buffet. Rounds with seating for 10 per table. Set for 310. Need Easel outside Room | Tuscan Buffet, Minestrone Soup, tossed greens, manicotti, chix marsala, polenta, ratatouille, bread & Tiramisu with Coffee service (we do have 4vegitarians & 1 strawberry allergy attending) | Simple Stage Set with Podium LCD Projection Package Technician Laptop Wireless Lavaliere Mic | All Conference Speaker
| Lunch |  |  |  | 300 |  | On Own
| Technical Sessions Ballroom #1 | Ballroom 1 | 1:30pm - 3:00pm | Rich Newhart 720-468-1364 | 250 Each (Maximum capacity) | Theater. Need Easel outside Room |  | AV 4 (screen), 2 rental computers (primary & back up), 1 projector, 1 podium, 1 audio set-up, 2 AV tech (1 for audio & 1 for computer)
| Technical Sessions Ballroom #3 | Ballroom 3 | 1:30pm - 3:00pm | Rich Newhart 720-468-1364 | 250 Each (Maximum capacity) | Theater. Need Easel outside Room |  | AV 5 (screen), 2 rental computers (primary & back up), 1 projector, 1 podium, 1 audio set-up, 2 AV tech (1 for audio & 1 for computer)
| Afternoon Break | Exhibits areas and Ballroom Lobby | 3:00pm - 3:30pm | Julie Sibthorp 801-643-9398 | 480 | Reception/Buffet. Need Easel by Food stations. Food I Ballroom Lobby & Atrium Level | Cookies, Assorted Candy Bars, Whole Fruit / Coffee (Regular & Decaf), Tea, Assorted Soft Drinks
| Technical Sessions Ballroom #1 | Ballroom 1 | 3:30pm - 4:50pm | Rich Newhart 720-468-1364 | 250 Each (Maximum capacity) | Theater. Need Easel outside Room |  | AV 4 (screen), 2 rental computers (primary & back up), 1 projector, 1 podium, 1 audio set-up, 2 AV tech (1 for audio & 1 for computer)
| Technical Sessions Ballroom #3 | Ballroom 3 | 3:30pm - 4:50pm | Rich Newhart 720-468-1364 | 250 Each (Maximum capacity) | Theater. Need Easel outside Room |  | AV 5 (screen), 2 rental computers (primary & back up), 1 projector, 1 podium, 1 audio set-up, 2 AV tech (1 for audio & 1 for computer)
| Social Event - Octoberfest | Tent | 5:45pm - 8:30pm? | Jason Blake 435-901-1169 | 305 (Ticketed Event) | Buffet. 32 Rounds with seating for 10 per table. Set for 320. Heaters provided by Snowbird. Need Easel outside tent. 3 Bars | 6:30pm - Buffet Open: Oktoberfest Theme Buffet: salad, german potato salad, sauerkraut, bratwurst, beef rouladen, potato pancakes, seasonal veggies, rolls, apple strudel. Bar w/ 2 drink tickets | Stage provided by Snowbird. SE to bring own sound system. Will need power provided by Snowbird. | Salzburger Echo 6:00pm - 6:40pm playing during recpetions - 6:40pm - 7:00pm (break) - 7:00pm - 8:00pm show.
| Security (Need 2 snowbird Security guards) | Lock Ballroom 2, patrol Mezz & Atrium Overlook & Golden CLiff | 5:00pmMON - 8:00amTUE | Julie Sibthorp 801-643-9398
| Snowbid Staff to transport Tuesday's Core to Core Presentation Areas | Pick up at Loading Dock/Storage area and take to Magpie & Golden Cliff | 5:00pm | Rich Newhart 720-468-1364 Mike Laine 824-9013 |  | Need 2 staff at $40 per hour to transfer Core (as directed by AAPG staff) to Wasatch A&B & Golden Cliff
| Snowbid Staff to transport Core from Core Presentation Areas to Loading Dock/Storage Area | Magpie A/B & Golden Cliff to Loading Dock for GES pick-up | 5:30pm/ 6:00pm | Rich Newhart 720-468-1364 Mike Laine 824-9013 |  | Need 2 staff at $40 per hour to transfer Core (as directed by AAPG staff) to Wasatch A&B & Golden Cliff
| GES to transfer Core from Snowbird to storage area | take to Utah Core Research Center | 6:30pm
Day 5, Tuesday October 9, 2007
| Registration | Coat Room | 7:00am - noon | Greg Wood 680-7663 |  | Skirted Tables 2-3, chairs 4-5. Need Easel |  | Internet Connection
| Conference office | Little Pine | 6:30am-8pm |  | 4 | Two tables and 4-5 chairs |  |  | Internet Connection
| Speakers Breakfast | Maybird | 6:30am - 7:30pm | Rich Newhart 720-468-1364 | 60 | Banquet/Buffet 6 Rounds of 11. Need Easel outside Room | Breakfast Buffet BB3
| Spouse Breakfast | Summit - 10th Floor | 8:00am - 9:30am (time change) | Tina Blake 435-901-8328 | 100 | Banquet/Buffet | Breakfast Buffet BB3
| Spouse Hospitality | Summit - 10th Floor | 8:00am-5:00pm | Tina Blake 435-901-8328 | 100 | Lounge, Flowers, & Newspaper. Easel outside room.
| AAPG RMS Breakfast | Superior A&B | 6:00am - 8:30am Food out from 6am - 7:30am | Steve Schamel | 32 | Banquet U shaped. Extra chairs along back walls for observers. Easel outside room. | Breakfast Buffet- BB1
| IP Prospect Room | White Pine | 8:00am - 5:00pm |  |  | 6 draped table & 12 chairs. Water service on side table.
| Technical Sessions Ballroom #1 | Ballroom 1 | 8:00am - 9:50am | Rich Newhart 720-468-1364 | 250 Each (Maximum capacity) | Theater. Need Easel outside Room |  | AV 4 (screen), 2 rental computers (primary & back up), 1 projector, 1 podium, 1 audio set-up, 2 AV tech (1 for audio & 1 for computer)
| Technical Sessions Ballroom #3 | Ballroom 3 | 8:00am - 9:50am | Rich Newhart 720-468-1364 | 250 Each (Maximum capacity) | Theater. Need Easel outside Room |  | AV 5 (screen), 2 rental computers (primary & back up), 1 projector, 1 podium, 1 audio set-up, 2 AV tech (1 for audio & 1 for computer)
| Technical Sessions Ballroom Wasatch A&B | Wasatch A&B | 8:00am - 9:30am | Rich Newhart 720-468-1364 | 154 (Max Capacity) | Theater. Need Easel outside Room |  | Project to large screen with 2 smaller screen feeds (see drawing), 2 rental computers (primary & back up), 1 projector, 1 podium, 1 audio set-up, 2 AV tech (1 for audio & 1 for computer)
| Exhibit Areas Open | Ballroom 2, Mezanine Lobby, Atrium Overlook, Golden Cliff, | 8:00am - 5:00pm | Craig Morgran 815-1967 | 32 booths |  |  | Routers for wireless internet
| Poster Area Open | Magpie A&B, | 8:00am - 5:00pm | Rich Newhart 720-468-1364 | 10 Posters
| Morning Break | Exhibit areas and Ballroom Lobby | 9:30am - 10:15am | Julie Sibthorp 801-643-9398 | 480 | Reception/Buffet. Easle by Food Station (2 ffod stations) | Muffins, Cinnamon Rolls, Fruit Yogurt / Coffee (Regular & Decaf), Tea, Assorted Soft Drinks
| Technical Sessions Ballroom #1 | Ballroom 1 | 10:15am - 11:35pm | Rich Newhart 720-468-1364 | 250 Each (Maximum capacity) | Theater. Need Easel outside Room |  | AV 4 (screen), 2 rental computers (primary & back up), 1 projector, 1 podium, 1 audio set-up, 2 AV tech (1 for audio & 1 for computer)
| Technical Sessions Ballroom #3 | Ballroom 3 | 10:15am - 11:35pm | Rich Newhart 720-468-1364 | 250 Each (Maximum capacity) | Theater. Need Easel outside Room |  | AV 5 (screen), 2 rental computers (primary & back up), 1 projector, 1 podium, 1 audio set-up, 2 AV tech (1 for audio & 1 for computer)
| Technical Sessions Ballroom Wasatch A&B | Wasatch A&B | 10:15am - 11:35pm | Rich Newhart 720-468-1364 | 154 | Theater. Need Easel outside Room |  | Project to large screen with 2 smaller screen feeds (see drawing), 2 rental computers (primary & back up), 1 projector, 1 podium, 1 audio set-up, 2 AV tech (1 for audio & 1 for computer)
| Lunch and tram ride | Tram Deck (Back up is Cottonwood Room) | 11:45am-1:45 pm | Jason Blake 435-901-1169 Tina Blake 435-901-8328 Jessica Allen 891-8248 | 260 | Guests to pick up box lunches on Tram Deck before loading tram. | Box Lunch available at base of tram (Luncheons to Go)81 Roast Beef,81 turkey. 81 chicken &15 vegi. | Portable Outdoor Sounds system at top of tram. $150.00 per day | Tram rental for 2 hours (11:45pm - 1:45pm). Volunteers at tram to take tickets.
| Technical Sessions Ballroom #1 | Ballroom 1 | 2:00pm - 4:10pm | Rich Newhart 720-468-1364 | 250 Each (Maximum capacity) | Theater. Need Easel outside Room |  | AV 4 (screen), 2 rental computers (primary & back up), 1 projector, 1 podium, 1 audio set-up, 2 AV tech (1 for audio & 1 for computer)
| Technical Sessions Ballroom #3 | Ballroom 3 | 2:00pm - 4:10pm | Rich Newhart 720-468-1364 | 250 Each (Maximum capacity) | Theater. Need Easel outside Room |  | AV 5 (screen), 2 rental computers (primary & back up), 1 projector, 1 podium, 1 audio set-up, 2 AV tech (1 for audio & 1 for computer)
| Exhibitor Reception | All exhibit areas and Golden Cliff | 4:00pm - 5:00pm | Julie Sibthorp 801-643-9398 | 400 | Reception /Buffet. Food Station #1 in Ballroom Lobby. Food Station #2 in Atrium Overlook. 1 Bar in Ballroom #2 and 1 Bar in Atrium Overlook. Eales by Food Stations. | Station #1 & 2- Totilla Chips, salsa & Guac, Chicken Satay, Brucheetta 2 Cash Bars 3 bartenders & 3 ticket sellers (1 drink ticket given to attandees)
| Exhibitor & GES Tear Down | All exhibit areas | 5:00pm - 9:00 pm | Julie Sibthorp 801-643-9398
| GES to be at Snowbird Center to pick up 2 pallets of core | Snowbird Center | 5:00pm | Julie Sibthorp 801-643-9398 Mike Laine 824-9013
| GES to load pallets of core onto truck | Cliff Lodge Loading Dock | 5:30pm | Julie Sibthorp 801-643-9398 Mike Laine 824-9013
| Snowbid Staff to transport Core from Core Presentation Areas to Loading Dock for GES pickup | Magpie A/B & Golden Cliff to Loading Dock for GES pick-up | 5:30pm | Rich Newhart 720-468-1364 Mike Laine 824-9013 |  | Need 2 staff at $40 per hour to transfer Core (as directed by AAPG staff) to Wasatch A&B & Golden Cliff
| GES to transfer Core from Snowbird to storage area | take to Utah Core Research Center | 6:15pm | Julie Sibthorp 801-643-9398 Mike Laine 824-9013
| GES arrive at Utah Core Research Center for unloading | take to Utah Core Research Center | 7:15pm | Mike Laine 824-9013
| Presidents Reception | Atrium Restaurant | 6:00pm - 9:00pm | Steve Schamel & Julie Sibthorp 801-643-9398 | 110 | Reception/Buffet.Open bar (wine & beer only) | R5 Whole Roasted Tenderloin carving station; R7 Samon Wellington, R14 cheese display, R16 crudites display, R17Baked Brie and R19 Choc Fondue . Add Ceaser Salad. Open Bar (beer & Wine only). J Lohr Cabernet & Schlumberger Pino Blanc |  | Yes (backgroud music)
Day 6, Wednesday October 10, 2007
| Guest Departure |  | On Own
| Field Trip #3 Geology of Central Ut | Main Entrance | 7:30am |  | bottom of escalators
Day 8, Friday, October 12, 2007
| Return for Field Trip #3 | Main Entrance | 18:00 |  | bottom of escalators

## GES Core Transportation Schedul
AAPG - Rocky Mountain Section Core Transportation Agenda
|  | LOCATION | HOURS
Day 1 - Friday, October 5, 2007
| GES to transfer Core to Snowbird | Utah Core Research Center | 9:00am pick -up; depart 9:30am
| Snowbid Staff & UCR staff to transport Core to Core Presentation Areas | Pick up at Loading Dock at Snowbrid Center from GES to location of Short Course | 10:30am (GES arrives at Snowbird Center)
Day 2 - Saturday, October 6, 2007
Day 3 - Sunday, October 7, 2007
| GES - Set up Booths & Poster Boards | Ballroom 2, Mezanine Lobby, Atrium Overlook, Golden Cliff, Magpie A&B | 6:00am - 12:00pm
| Core/Poster Set Up By GES | Magpie A&B & Golden Cliff | 6:00am - Noon
| GES to transfer Monday's Core to Snowbird | Utah Core Research Cente to Cliff Lodge Loading Dock | Pick up at 12:00pm. Will take 20 min to load truck. | 2 oe 3 pallots
| GES arrives at Cliff Lodge. Snowbid Staff & UCR staff& to assist in transport Core to Golden Cliff & Magpie | Pick up at Cliff Lodge Loading Dock from GES - take ot Golden Cliff & Magpie | 1:30pm (GES arrives)
| Snowbird Staff & UCR staff to pick up & transport Core from CottonWood D in Snowbird Center to Loading Dock for GES pickup | Cottonwood D - loading dock at Snowbird Center | 3:00pm
| Snowbird Staff & UCR staff to pick up & transport Core from CottonWood D in Snowbird Center to Loading Dock for GES pickup | Cottonwood D - loading dock at Snowbird Center | 4:30pm
| GES to go to Snowbrid Center at 3:30pm & pick up core from short course & bring some of the core to Cliff Lodge | Cliff Lodge - to Snowbird Center - to Cliff Lodge | 3:30pm
| GES depart for Utah Core Research Center | take to Utah Core Research Center | 4:00pm
| GES arrive at Utah Core research Center (UCR staff to unload) | Utah Core Research Center | 5:00pm
Day 4 - Monday, October 8, 2007
| GES to transfer Core to Snowbird | Pick up at Utah Core Research Center (UCR staff to load onto truck) | 3:30pm pick up. Will take 20 -30 minutes to load | 2 pallots
| Snowbid Staff & UCR staff to transport Core from Core Presentation Areas to Loading Dock for GES pickup | Magpie A/B & Golden Cliff to Loading Dock for GES pick-up | 5:00pm
| add pick up at Snowbird center & Bring back |  | 5:20pm - pick up core at
|  | Back to center | 6:30pm
| Snowbid Staff & UCR staff to transport Tuesday's Core to Core Presentation Areas | Pick up at Loading Dock from GES and take to Magpie & Golden Cliff | 6:00pm (GES arrives)
| GES to transfer Core from Snowbird to storage area (UCR staff to unload) | take to Utah Core Research Center | 6:30pm
Day 5, Tuesday October 9, 2007
| Exhibitor & GES Tear Down | All exhibit areas | 5:00pm - 9:00 pm
| Snowbid Staff & UCR staff to transport Core from Core Presentation Areas to Loading Dock for GES pickup | Magpie A/B & Golden Cliff to Loading Dock for GES pick-up | 5:30pm
| GES Arrives at loading dock |  | 5:45pm
| GES to transfer Core from Snowbird to storage area | take to Utah Core Research Center | 6:00pm
| GES arrive at Utah Core Research Center for unloading (UCR staff to unload) | Arrive at Utah Core Research Center | 7:00pm