## Slide 1
Rocky Mountain Section Meeting Timeline
Meeting
Final
Deadline
Abstract
Deadline
(but gets
Extended)
Abstract
Submission
Opens
Tech.
Publicity
Website
AAPG Email Blast to RMS
& we notify other societies of:
Meeting announ w/ below
AAPG Email blast &
Notify other societies:
Final tech themes
Final sess chairs
Abstract sub. open
Call for Papers
AAPG Email blast &
Notify other societies:
Abstract deadline coming
Abstract deadline extended
Any changes in program
Start working on Final Announcement
exclusive of technical program.
Mail out Final Announcement
to RMS section
This opens mail-in registration.
Open online
registration
Prepare Program with
Abstracts. Print. Send
to meeting facility.
Open link to
ScholarOne
(Abstract
Service)
Update website with
new info on all aspects of
meeting as get them.
Decide:
Technical Session Themes
Recruit chairs
Distribute flyer at AAPG Nat Mtg w:
Dates / Location
Proposed Technical Session Themes
Possible short courses
Proposed field trips
Proposed social events
Other amenities of location / buzz
Form Org com.
Decide loc/ dates
Contract for facility
Discuss tech themes,
FTs, SCs, social activ.
Make prelim timeline.
Run ¼ page ads in AAPG Explorer and also ads in RMAG” Outcrop”
Sponsorship
Start soliciting sponsors.
Mail out letters and form.
Specify deadline for sponsors
to be acknowledged in FA / PwA
Send list of sponsors
and their digital logos
to person doing Final
Announcement
Notify presenters of acceptance / rejection.
Also location & time of talks, where & how
to load powerpoint talks, dimensions of
potser space, hours to be at their posters,
loc & time of speaker’s bkfst, etc.
Session chairs
review papers,
Tech chairs assign
orphans, draw up
program.
Ask all chairs for
budget estimates
Finalize estimates of
expenditures
Determine registration fee: Registration income plus some
minimum of sponsorship and exhibitor income must cover
estimated expenditures with a cushion for overruns.
Send final list of sponsors and their digital logos
to person doing PwA and to Signs chair.
Exhibits
Start soliciting exhibitors.
Mail out letters and form.
Specify deadline for exhibitors
to be included in PwA
Contact rental companieswho provide
piping, drape and poster backing.
Find out costs for rental including
transportation, setup, teardown.
Determine cost to be charged to
exhibitors. 2-tieredfor commerical
& non-profits. Costs for security.
Make a powerpoint slide to be shown
between talks thanking all the sponsors
(with their logos).
Estimate
Budget (inclu
Speaker gifts,
Poster booth
Rental, IT
support, etc.)
Set up Meeting
Website
Send floorplan & list
To person doing FA.
Get security guards.
Work with Exhibitors to set
up & tear-down booths.
Make sure guards in place.
Open Reg.
Open Abstr. Sub.
Close Abstr. Sub.
Feb 1 ‘10
Feb 15 ‘10
March 15‘10
Aug/Sept ‘09(?)

## Slide 2
Rocky Mountain Section Meeting Timeline
Form Org com.
Decide loc/ dates
Decide facilites
Discuss tech themes,
FTs, SCs, social activ.
Make prelim timeline.
Ask all chairs for
budget estimates
Finalize estimates of
expenditures
Determine registration fee: Registration income plus some
minimum of sponsorship and exhibitor income must cover
estimated expenditures with a cushion for overruns.
Field
Trips
Decide Field Trips
and leaders
For each trip need:
budget estimate / determine price of trip / min # participants
standardized write-up for web & F.A.
deadline for cancelling trip if registration #s too low
(tied to lodging and transportation contract backout dates)
Make transportation & lodging arrangements, sign contracts.
Make sure FT insurance
waivers are included in
registration section
of F.A. and website.
Drop FTs with enrollment below break-even number.
Notify participants by email.
Short
Courses
Solicit SCs
and instructors
(check PTTC, AAPG
Explorer, service
Companies, etc)
For each course need:
budget estimate / price / min # students
standardized write-up for web & F.A.
deadline for cancelling SC if registration #s too low
Drop SCs with enrollment below break-even number.
Notify participants by email.
Awards &
Judging
Find out previous year’s winners
Of the three awards from RMS
Website / officers.
Provide a budget for:
award plaques
judging packets
judges gifts
Make sure judging checkbox
is included in registration
form in FA and website
Distribute judging packets & ribbons at registration.
Collect completed forms.
Announce winners, pass on info to RMS officers.
Prepare a few slides for
Opening Ceremony & Awards
Prepare signage
(powerpoint files).
Print. Mount.
Signage
Place signs during meeting.
Change daily.
Registration
Finance
Venue walkthrough
Submit budget estimate
Staff Registration table
Send $$ to Treasurer
Process mail-in and
Online registrations
Prepare
registration form
Finalize predicted meeting costs
Determine registration fees.
Pay incoming bills.
Deposit incoming reg. fees.
Send final accounting
to RMS Pres. & Treas.